|  |  |  |  |
| --- | --- | --- | --- |
| Task Name | Duration | Start | Finish |
| **Adding State Level /Permissions for School Level users** | **20 days** | **Mon 4/27/15** | **Fri 5/22/15** |
| Development | 3 wks | Mon 4/27/15 | Fri 5/15/15 |
| Testing | 1 wk | Mon 5/18/15 | Fri 5/22/15 |
| **User Setting Interface Enhancements** | **15 days** | **Mon 5/18/15** | **Fri 6/5/15** |
| Development | 1 wk | Mon 5/18/15 | Fri 5/22/15 |
| Testing | 1 wk | Mon 5/25/15 | Fri 5/29/15 |
| REMS TA Center User Testing | 1 wk | Mon 6/1/15 | Fri 6/5/15 |
| **Adding Interface Enhancements** | **17 days** | **Mon 5/25/15** | **Tue 6/16/15** |
| Development | 3 wks | Mon 5/25/15 | Fri 6/12/15 |
| Testing | 1 wk | Wed 6/10/15 | Tue 6/16/15 |
| **Exported Plan Enhancements** | **10 days** | **Mon 6/15/15** | **Fri 6/26/15** |
| Development | 1 wk | Mon 6/15/15 | Fri 6/19/15 |
| Testing | 1 wk | Mon 6/22/15 | Fri 6/26/15 |
| **Integration** | **17 days** | **Mon 6/22/15** | **Tue 7/14/15** |
| Development | 2 days | Mon 6/22/15 | Tue 6/23/15 |
| Testing | 3 wks | Wed 6/24/15 | Tue 7/14/15 |
| **SQL Server Capability** | **5 days** | **Wed 6/24/15** | **Tue 6/30/15** |
| Development | 3 days | Wed 6/24/15 | Fri 6/26/15 |
| Testing | 2 days | Mon 6/29/15 | Tue 6/30/15 |
| REMS TA Center User Testing | 2 wks | Wed 7/15/15 | Tue 7/28/15 |
| **Deployment Package** | **6 days** | **Wed 7/29/15** | **Wed 8/5/15** |
| Development | 1 day | Wed 7/29/15 | Wed 7/29/15 |
| Testing | 1 wk | Thu 7/30/15 | Wed 8/5/15 |